{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":45,"n_cols":7,"rows_kept":45,"merged":[[2,0,5,0],[2,1,5,1],[7,0,10,0],[7,1,10,1],[11,0,12,0],[11,1,12,1],[13,0,16,0],[13,1,16,1],[17,0,24,0],[17,1,24,1],[23,6,24,6],[25,0,28,0],[25,1,28,1],[29,0,31,0],[29,1,31,1],[32,0,33,0],[32,1,33,1],[35,0,38,0],[35,1,38,1],[39,0,41,0],[39,1,41,1]],"flags":["formulas_cached_only"]}
[]
["序号","工作内容","具体工作任务","时限要求","责任单位   和人员     (A岗)","相关责任人 （B岗）","配合处室及人员"]
[1,"进一步研究和完善新农合运行机制，加强监督管理，不断扩大受益面，提高收益水平","切实做好全省新农合管理日常工作","全年","合管中心",null,"张 云"]
[null,null,"做好新农合数据统计分析，按时完成卫生部各类报表报送","每月、每季度","应  玥","张 云","张 云"]
[null,null,"逐步扩大门诊统筹试点，年内各市（州）选择一个县（区）试点，逐步提高新农合基金使用率和参合农民受益水平","全年","张  云","蒋雪萍","合管中心"]
[null,null,"加强调研，做好新农合信息收集整理，完成5期《新农合工作信息》编写印发，加强市州、县区间的交流","全年","应  玥","张 云","张 云"]
[2,"定点医疗机构管理","转发卫生部《关于规范新农合定点医疗机构管理的意见》，进一步完善我省新农合定点医疗机构管理的的政策措施","卫生部发文1个月内","张  云","蒋雪萍","合管中心"]
[3,"新农合基金监管","起草印发《关于进一步规范全省新型农村合作医疗补偿报销制度的通知》","3月份","张  云",null,"合管中心"]
[null,null,"全省2009年度新农合工作检查（市、县、定点医疗机构自查；市州互查；省级督查）","自查3月日4月30日","合管中心",null,"张 云"]
[null,null,"全面实行参合农民在统筹县（区）内定点医疗机构自主就医、出院及时结报的办法","11月30日前","合管中心",null,"张 云"]
[null,null,"逐步推行省、市级定点医院统一补偿方案，探索省市、级定点医院现场垫付报销、定期结算制度，年内4个左右的市（州）推行参合农民在市（州）级定点医疗机构出院即时结报","11月30日前","合管中心",null,"张 云"]
[4,"加强新农合经办机构建设","新农合信息化建设建设","全年","合管中心",null,"张 云"]
[null,null,"市、县经办机构、定点医疗机构人员培训","11月底前","合管中心",null,"张 云"]
[5,"新农合财政补助资金申请拨付工作","督促市、县补助资金拨付到位并上报相关资料","3月底前","合管中心",null,"张 云"]
[null,null,"申请省级财政补助资金并拨付到位","4月底前","合管中心",null,"张 云"]
[null,null,"协调财政部驻甘专员办审核我省地方财政补助资金到位情况","5月底前","合管中心",null,"张 云"]
[null,null,"申请中央财政补助资金并转拨各县（区）","5月底前","合管中心",null,"张 云"]
[6,"   卫生支农","1、制定甘肃省实施万名医师支援农村卫生工程三级甲等医院对口带教县级卫生技术人员实施方案","3月11日-3月31日","蒋雪萍","张蜀青","医政处  人事处  科教处"]
[null,null,"2、制定进一步加强万名医师支农医疗队员考核管理工作的意见","3月11日-3月31日","蒋雪萍","张蜀青"," 人事处"]
[null,null,"3、制定一个调查表，对全省实施万名医师支援农村卫生工程的支、受援医疗卫生机构、项目县卫生局、支农队员进行一次调查，探索卫生支农长效机制","4月1日-4月10日","蒋雪萍","张蜀青"]
[null,null,"4、组织宣讲团，宣讲优秀支农队员的感人事迹；组织记者团进行实地采访；编写优秀支农队员先进事迹书籍","4月1日—12月31日","蒋雪萍","张蜀青"," 办公室"]
[null,null,"5、下拨2009年度支农医疗队员补助经费","4月1日-4月30日","蒋雪萍","张蜀青"," 规财处"]
[null,null,"6、召开卫生支农中期工作会议","8月21日-8月24日","蒋雪萍","张蜀青"]
[null,null,"7、抽调2010年支农医疗队员","10月10日-11月30日","蒋雪萍","张蜀青","人事处  医政处"]
[null,null,"8、开展2009年支农队员年底考核、评优等工作","11月10日-12月31日","蒋雪萍","张蜀青"]
[7,"乡镇卫生院等级评审","1、下发《甘肃省乡镇卫生院等级评审标准（试行）》","3月1日-3月31日","蒋雪萍","张蜀青"]
[null,null,"2、指导各县乡镇卫生院等级评审工作","8月1日-11月30日","蒋雪萍","张蜀青","农卫协"]
[null,null,"3、开展乡镇卫生院复评工作","3月11日-11月31日","蒋雪萍","张蜀青","农卫协"]
[null,null,"4、核发乡镇卫生院等级证书和匾牌","11月31日-12月31日","蒋雪萍","张蜀青"]
[8,"农村卫生协会","1、成立全省农村卫生协会，落实办公地点和经费            ","1月1日-2月28日","蒋雪萍","张蜀青"]
[null,null,"2、指导卫生协会开展卫生支农、乡镇卫生院评审等具体工作","3月31日-12月31日","蒋雪萍","张蜀青"]
[null,null,"3、创办甘肃基层卫生杂志","3月11-4月30日","蒋雪萍","张蜀青","中医学院"]
[9,"乡镇区卫生院、村卫生室基本情况调查","完成全省乡镇卫生院、村卫生室基本情况调查","4月底前","张  云","蒋雪萍"]
[null,null,"完成乡镇卫生院、村卫生室设备采购计划和下拨工作","4月底前","张  云","蒋雪萍","规财处"]
[10,"初级卫生保健","按照卫生部的有关要求开展工作","全年","蒋雪萍","张蜀青"]
[11,"乡村医生执业证书换发","下发通知，做好换证前前期准备工作","3月底前","张蜀青","张  云"]
[null,null,"完成新证申领人员资料审核工作","4月10日前","张蜀青","张  云"]
[null,null,"审核发证","4月10日-4月30日","张蜀青","张  云"]
[null,null,"汇总证书发放情况，完成工作总结","5月底前","张蜀青","张  云"]
[12,"基层卫生工作人员、技术人员培训","举办甘肃省2009年乡镇卫生院管理骨干培训班","6月10日-6月30日","张蜀青","张  云","省卫校"]
[null,null,"举办全省县（区、市）卫生局局长培训班","7月20日-7月22日  ","张蜀青","张  云","省卫校"]
[null,null,"举办乡镇卫生院设备操作人员培训班（包括B超、心电图、X光机、血球计数仪、半自动生化分析仪等培训）四期","9月16日--11月20日分四期进行","张蜀青","张  云","省卫校"]
[13,"香港嘉道理项目","按照卫生部香港嘉道理项目的具体安排开展工作","1月1日—12月31日","蒋雪萍","张蜀青"]
[14,"上海世茂援建卫生院项目","按照上海世茂援建卫生院项目协仪书开展工作","1月1日—12月31日","蒋雪萍","张蜀青"]
[15,"李兆基基金项目","按照温暖工程李兆基基金项目完成计划","5月10日-11月30日","张蜀青","张蜀青"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}